# Terms of Reference

# Oporajita Entrepreneurial (Business Incubation and Management) Training

| Particulars | Date/Time |
| --- | --- |
| TOR Publication date | 3 May 2026 |
| Virtual Pre-bid Meeting on ToR for assessment (To participate in this meeting interested firms are requested to send their interest through email by 10th May 2026 to bangladesh.procurement@ideglobal.org Google link will be provided only to interested firms through the email address from which request has been submitted. | 11 May 2026 |
| Deadline for submission of Final proposals (technical and financial, along with the firm’s proposal) by interested qualified agencies to bangladesh.procurement@ideglobal.org | 17 May 2026, 11:00 PM (BST) |

1. Organization Background

iDE is an international NGO with over 42 years of experience in designing and delivering market-based anti-poverty programs in 11 countries. We are a world leader in making markets work for the poor as well as the longest-established market development specialist INGO in Bangladesh. iDE believes that markets can be a powerful force for improving smallholder prosperity by creating income and livelihood opportunities for poor rural households.  iDE Bangladesh currently has multiple projects in agricultural markets, water, sanitation, and hygiene (WASH), and access to finance with a focus on women’s economic empowerment and climate-smart technologies.

2. Project Background

Oporajita, a Collective Impact Initiative, for the Future of Work for Bangladesh, is a 29-month (2025-2028) project funded by the H&M Foundation, with the vision to empower women garment workers (WGWs) and safeguard livelihoods from the impact of automation and digitalization in the textile industry. Following the completion of phase i, in this second phase of the project iDE’s goal for Oporajita is to improve the entrepreneurial capacity of 1,400 out-of-work women garment workers (WGWs), particularly those located in the Dhaka division (Gazipur and Savar) by equipping them with advanced entrepreneurial skills, market and credit linkage support, and opportunities to enter high-growth climate-smart sectors to increase their incomes over the duration of the project.

The project aims to achieve three major outcomes to ensure-

(i) Out-of-work WGWs are able to access and utilize appropriate enterprise development services, which enable them to start and/or further improve their business in target sectors; 
(ii) Out-of-work WGWs are able to utilize, access, and uptake a range of critical financial products, services, capacity-building measures, and digital/analog marketplaces to enhance their businesses; 
and (iii) Out-of-work WGWs adopt green practices through and have access to seed funding, and green financing, enabling them to launch sustainable enterprises.

3.  About the Assignment

iDE-Bangladesh is looking for a joint venture partnership agreement (JVA) with a professionally skilled Business Development Service (BDS) provider to improve the practical entrepreneurial competencies of Oporajita’s cohort of 1,400 out-of-work WGWs in entrepreneurship and other growth-oriented business operations and financial management. With the enhanced entrepreneurial capacity of out-of-work WGWs as the overall objective, the BDS provider will facilitate high-quality business incubation and management training to build the capacity of the target group. After this training, which is a transformative tool for unlocking the potential of aspiring entrepreneurs, iDE will conduct direct mentorship with the trained women to support their business aspirations and growth. This is an assignment that will start in June  2026 and it is expected that all deliverables will be completed before 31st May 2027.

The partnership is open to BDS providers that meet the following criteria:

- Demonstrated ability to contribute to the assignment on a cost-sharing basis of at least 50:50 for agreed activities (iDE resource sharing can go up to 50% maximum, the JVA partner could show the contribution as matching funds, in-kind contribution, or third-party contribution)

- Proven experience in developing and delivering entrepreneurship and business training modules for women entrepreneurs, including but not limited to, the following sectors:

  - Cow, Poultry & Goat Rearing (Commercial)

  - Group Business Initiatives (Handicrafts, Beautification, Tailoring)

  - Curd & Milk-Based Products

  - Waste Collection & Recycling (Bhangari)

  - Jute (Textile Scrap) Upcycling

  - MHM (Menstrual Hygiene Management) Products

  - Vegetable & Mushroom Farming

  - Home-Based Shop (e.g. laundry, grocery etc)

  - Food Carts, Home-Based Food Provider (Lunch)

  - Honey Harvesting

  - Niche Medical Supplies

- Capacity and proven track record in identifying, screening, and mobilizing training participants at training venues in project locations.

- Ability to provide direct or indirect financial or working capital support to trained women entrepreneurs either through their own financing mechanism or through linkage/partnership with a financial service provider (FSP), to support further business development.

The assignment will help fulfill the key outcomes of the project with targeted entrepreneurial sectors that include vegetable farming, poultry/cow rearing, tailoring, bakery, waste upcycling, handicrafts, etc. The training will be divided into two curriculums/modules-

- Advanced training with refresher courses for 400 women entrepreneurs from Oporajita phase I.

- Basic entrepreneurship training for 480 new out-of-work women garment workers/aspiring entrepreneurs selected for Phase II.

The key competencies for this assignment are:

- Conduct a Training Needs Assessment (TNA) to identify critical training content and support needs, focusing on business management, financial literacy with digital financial tools, production and sales planning, circular business practices, life skills, and decent work.

- Co-create a selection process for phase I entrepreneurs who demonstrate core traits such as resilience, initiative, leadership, and creativity. Evaluation will focus on a practical problem-solving mindset and the candidate's openness to coaching.

- Mobilize the selection of 480 new aspiring entrepreneurs for training in 5 Upazilas- Savar Sadar, Dhamrai, Gazipur Sadar, Sreepur, Kaliakoir.

- Develop and customize an iDE MSME Entrepreneurship and Business Management Training (BMT) for both basic and advanced modules aligned with high-growth climate-smart sectors.

- Facilitate a 1-day Training of Trainers (ToT) to build the capacity of trainers and iDE/Oporajita field staff.

- Improve business management abilities of out-of-work WGWs through Basic Entrepreneurial (Business Incubation and Management) Training, which includes but is not limited to:

    - What is an Entrepreneur? What is a vision board?

    - Business and Entrepreneurship Development (Business Model Canvas and Business Plan)

    - Business finance management, profit margin calculation

    - Marketing research, Marketing Mix, and Marketing plan

    - Sector-specific technical modules

- Additionally, the second Phase of Oporajita aims to address climate challenges, sustainability and just-transitions in microbusiness by leveraging the Green Growth Strategy, as developed by iDE, to support out-of-work women garment workers and women entrepreneurs in transitioning to "green" sectors, products, and services. Therefore, both basic and advanced training will incorporate specialized sessions on green business practices and circular economy principles.

- Facilitation of market linkages and access-to-finance opportunities for Oporajita’s entrepreneurs for business operations, expansion, and sustainability.  These activities will not only facilitate interactions among key market actors but also address critical business topics such as production, sales, marketing, taxation, licensing, and registration, ensuring the sustainable creation and growth of women-led enterprises. The project will bolster market linkage support through cross-learning visits, industry leader interactions, and one-on-one advisory sessions to create opportunities for buyer networking, bulk procurement of raw materials, and access to financial and non-financial services.

As a result, the expected outcomes from this partnership are given below. Please include a proposed methodology and a plan for achieving the partnership goals listed below within your proposal :

- 80% of trainees report improved capacity in business initiation, management, or expansion

- 70% report improved ability to cope with market shocks

- 50% demonstrate improved business management practices

- 80% report stronger business linkages with suppliers and buyers

- 70% report improved understanding of financial services

- 50% access loans or financial/in-kind support (through direct facilitation, joint partnership or linkage/facilitation)

- 60% of those in green/circular businesses actively adopt sustainable practices

To be considered successful, the BDS provider training activities must result in demonstrable improvements in out-of-work WGW’s practical business incubation and management competencies. It is the responsibility of the BDS provider to specifically define how the activities included in the training module will lead to measured improvements in specific knowledge, skills, and attitudes related to business management.

4. Major Responsibilities of the BDS provider

In consultation with the respective unit at iDE, the BDS provider will be mainly responsible for the following tasks or services:

| Phase | Responsibilities |
| --- | --- |
| Phase-I (Inception) June 15, 2026 | - Review the assignment’s scope of work and seek clarification, if necessary. - Organize a ‘kick-off’ meeting with Oporajita Dhaka and field staff to ensure alignment between the project team and BDS provider for efficient training delivery. Discuss with the project staff to understand their learnings and expectations from this consultancy. - Development of an assignment work plan - Review project documents and MSME Business Management Training (BMT) Module of iDE/Oporajita project from phase I. - Customize a Basic Entrepreneurial (Business Incubation and Management) Training module for the Oporajita project, as well as a training schedule. Use and/or adopt, where necessary, iDE’s existing training modules. Note: Project training is non-residential. - Develop an advanced training module with focused sessions on green business practices and circular economy principles. - Development of selection tools and field mobilization to select primary actors (out-of-work WGWs) for training. - Any revision/addition regarding the assignment should follow the requirements of iDE and must be addressed. - Assign a focal person who will work closely with the Oporajita project to ensure the proper delivery of any assignment. |
| Phase-II (Training) Jun’26 - Apr’27 | - Facilitate Training of Trainer (ToT) for the trainers and the iDE field team. - Lead and facilitate 16 batches of Basic training, and 13 batches of Advanced training, and 4 batches of specialised green module sessions. Each batch consists of 30 women. This training also includes conducting pre and post-assessments. - Arrange appropriate training venues, food/snacks, and stationery items required for the training. - Facilitate 10 post-training mentoring sessions (follow-up visits, virtual refresher sessions, sector-specific training, and market linkage activities). - Facilitate access-to-finance opportunities for 50% of trained entrepreneurs through formal or loans. |
| Phase-III (Closing) May 31, 2027 | - Deliver/Submit a final report documenting the assignment to the Oporajita team (max. 10 pages), capturing the training activities, list of participants, learnings/recommendations, photos, etc. - Organize a final meeting with the Oporajita team to provide assignment debriefing. |

5. Major responsibilities of iDE

iDE will provide the BDS provider with the necessary support to undertake and implement the assignment and execute the objective and tasks outlined in these Terms of Reference. Such responsibilities include the following:

- Provide initial briefing, orientation, and existing work plan overview;

- Provide project-related materials, business training modules, and other documents and reports;

- Provide feedback on different stages of the consultancy process: methodology, work plan, etc.;

- Participate in the ‘kick-off’ meeting with project field staff to ensure alignment between the project and the BDS  provider for efficient training delivery.

- Provide coordination support to the BDS provider  of the training events for the staff and target women;

- Organize a feedback session (can be virtual) with the project staff and comments from the consulting firm;

- Mention someone from the project as an assigned person to keep the coordination, and;

- Disburse payment as per payment tranches, after the acceptance of successful completion of specific deliverables.

7. Tentative Work Schedule

The BDS provider is expected to start work on or around 1st June 2026. This assignment will be completed by 31st May 2027, which includes the completion of all tasks in the assignment along with the submission of the deliverables as detailed in Section 6. Based on unavoidable circumstances, the period for conducting the assignment might change depending on the situation. The BDS provider is expected to be able to accommodate these changes without additional cost. The detailed work schedule/plan will be finalized upon mutual understanding from both parties during the kick-off meeting.

8. Proprietary Rights

Any document, information, or data entrusted to or produced by iDE in connection with this assignment shall be strictly confidential and cannot be used by the contract employee for any other purpose without the written consent of iDE. This provision shall remain valid even after the completion of this assignment. iDE-Bangladesh reserves the right to terminate this agreement at any time with the consultation of the contracted individual/firm. iDE will reserve the copyright of all produced materials and should be permitted to use them without a time limit.

9. Deliverables and Schedule of Payment

This assignment will start in June 2026 and continue till May 2027 (12-month long assignment). Tentatively, an average of 15 days may be required for each month. This work plan may be revised considering external situations and as per the needs of the project. The financial proposal should include the total cost of the service, consultancy fees detailing all transportation, logistics, and other costs (including accommodation and food expenses, etc.). The payment will be made in four (04) installments as follows:

| Sl No. | Key Activities | Deliverables | Timeline | Installment Percentage |
| --- | --- | --- | --- | --- |
| 1 | The contract is signed, and the Work Plan is developed and approved. | Deliverable 1 - 3: Signing the Contract, Provision of Detailed Work Plan, Kick-off Meeting, Approved Training Module, and Selection Tool. | Jun’26 | 25% of the Total Contract Value |
| 2 | Training ‘kick-off’ meeting is organized with the project field team. |  |  |  |
| 3 | The selection tool is developed, and scouting is initiated. |  |  |  |
| 4 | Training Module, Materials, and Schedule are developed and approved, and a 1-day training of trainers (ToT) is conducted. | Deliverable 4-5a: Training of Trainers, Basic and Advanced Training, Mentoring sessions, Market Linkage a nd Access-to-finance activities | Nov’26 | 30% of the Total Contract Value |
| 5a | Basic training- 8 batches Advanced training 6 batches + 4 specialised green business sessions 4 post-training mentoring sessions (follow-up visits, virtual refresher sessions, sector-specific training, and market linkage activities). |  |  |  |
| 5b | Basic training- 8 batches Advanced training 7 batches + 2 specialised green business sessions 6 post-training mentoring sessions (follow-up visits, virtual refresher sessions, sector-specific training, and market linkage activities). | Deliverable 5b: Basic and Advanced Training, Mentoring sessions, Market Linkage, and Access-to-finance activities | Apr’27 | 35% of the Total Contract Value |
| 6 | Final Report in the format agreed to by Oporajita is submitted, and a final assignment debriefing meeting with Oporajita is organized. | Deliverable 6: Final Report and Debriefing Meeting | May’27 | 10% of the Total Contract Value |

Note: Payment will be based on the timely submission of deliverables; however, the submission dates are tentative and can vary based on the discussion between the BDS provider and the iDE team.

Note: Government VAT and Tax regulation will be applied as per the norms of the organization, and these costs must be included in the financial proposal.

The following terms and conditions will apply:

- The payment will be made through account payee cheque/ wire transfer (account name, number, type, bank name, and branch name is required for wire transfer);

- As per the Government of Bangladesh VAT and tax regulation; International entities are taxed at 15% VAT (on contract amount) and 20% tax (on contract amount +VAT); National entities are taxed at 15% VAT and 7.5% tax, subject to Government laws.

- The Government VAT and tax regulation will be applied, and iDE Bangladesh will deduct all relevant VAT and Tax at source as per GoB rules.

- VAT Registration Certificate, TIN, Trade License, and Proof of Submission of Return (PSR) (if applicable) must be submitted before the agreement is signed.

- The selected BDS provider will abide by the other terms and conditions of iDE Bangladesh.

10. Eligibility Criteria

General experience and expertise required for this assignment are mentioned below:

- A minimum of 8-10 years of progressively responsible experience in the financial industry, business incubation and accelerator, agriculture, rural/ local economic development, market system development, market-based interventions, and enterprise development in a rural setting.

- Experience working with MSMEs, specifically leading women entrepreneurs' incubation programs, with proven experience in facilitating access to loans/capital from the formal sector.

- Sound understanding and experience in the labor market and women entrepreneurship in the Bangladesh context.

- Willing to work under pressure, maintain the quality of the work and deliverables.

- Experience working with international NGOs with relevant experience.

- Excellent analytical skills.

- Personal commitment, efficiency, and flexibility, together with the ability to work both independently under minimum supervision and with large, diverse project teams.

- Ability to create clear, logical data and other visualizations required.

- Ability and willingness to travel to remote areas

- Demonstration of logistical capability

- Experience working with the MSME (Medium Small &amp; Micro Enterprises), MFIs (Microfinance Institutions), Private sectors, and banks for local economic growth is preferable.

- Experience working on women-based activities, including but not limited to training, education, and employment opportunities at the district level of Dhaka Division is preferable.

- Demonstrated capacity and expertise to execute the activities, including the availability of equipment, contacts,

- and experience in undertaking similar assignments.

- Well-developed design and plan for executing the assignment, ensuring the quality work as mandated by iDE.

- This includes the approach to media engagement, a realistic timeline, critical milestones, dependencies, lines of

- communication, etc.

- Appreciative of delivering the final products in line with the set ToR within the agreed timeline.

- Relevant professional qualifications of key personnel / senior staff to conduct the proposed project, and the

- proposed management and team structure.

- Excellent interpersonal communication, easy presentation, good command of English, and Bangla.

11. Bid Submission and Evaluation Criteria

All proposals should include:

- Cover letter (maximum 01 page);

- Technical Proposal (maximum 03-05 pages) which should include:

  - Understanding of the assignment, methodology, and a detailed work plan

  - Relevant professional qualification and experience to carry out the assignment, ensuring the highest quality of the work

  - Links to samples of previous work (module development, entrepreneurship and climate-adaptation training, market linkages, access-to-finance, etc)  in a Google Drive folder

- Evaluation Metrics:

| S.N. | Content of the Proposal | Total Score |
| --- | --- | --- |
| 1 | Background/organizational profile of the applicant | 5% |
| 2 | Track record of earlier similar assignments (module development, entrepreneurship, RMG sector, climate-adaptation training, market linkages, access-to-finance, etc). Samples and recommendations resulting. Such work may be included in the Annex or linked to a Google Drive folder. | 15% |
| 3 | Goals are clearly outlined and contribute to the project's overall objectives. | 20% |
| 4 | Proposed methodology and approach | 15% |
| 5 | There is a clear and practical relationship between the defined problem and the solution proposed | 15% |
| 6 | Innovative products, services, and financing mechanisms are included | 10% |
| 7 | Detailed work plan outlining key activities over the assignment period | 20% |
| Total |  | 100% |

- Financial Proposal (maximum one page): Breakdown of all the cost estimates mentioning the different activities to complete the task. This should include, but not be limited to accommodation and travel costs (to the Oporajita project areas at the Upazila and District level under Dhaka Division), food expenses, and other items needed for the consultancy/service.

- Please also include:

  - Company profile

  - VAT Registration Certificate/BIN

  - TIN Certificate

  - Income Tax Certificate/Proof of Submission of Return (PSR )

  - Trade License Certificate/ Joint Stock Company Registration Certificate (if applicable)

Interested and qualified Business Development Service providers are asked to submit their Technical and Financial Proposals to bangladesh.procurement@ideglobal.org. Please write “Proposal for Oporajita - Entrepreneurial (Business Incubation and Management) Training 2026” in the subject line. The proposals should be submitted by 11:00 PM Bangladesh Standard Time (BST) on 17th May 2026. We are only able to consider electronic submissions. Only shortlisted BDS providers will be contacted and invited for a technical discussion.

Deadline: 17th May 2026 COB (11:00 PM BST).

Annex 1: The Content of the financial proposal

| Financial Proposal |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Name of the Organization |  |  |  |  |  | Date: |  |
| Address |  |  |  |  |  |  |  |
| SL | Items | No. of Persons | Unit(Day) | BDT per day or unit | Total Amount (BDT) | BDS provider Contribution (BDT) | iDE Contribution (BDT) |
| A | Remuneration |  |  |  |  |  |  |
| A1 | Team Leader |  |  |  |  |  |  |
| A2 | Study Coordinator |  |  |  |  |  |  |
| A3 |  |  |  |  |  |  |  |
| A4 |  |  |  |  |  |  |  |
| Sub Total |  |  |  |  |  |  |  |
| B | Travel and Accommodation |  |  |  |  |  |  |
| B1 | Two-way travel |  |  |  |  |  |  |
| B2 | Accommodation |  |  |  |  |  |  |
| B3 |  |  |  |  |  |  |  |
| B4 |  |  |  |  |  |  |  |
| Sub Total |  |  |  |  |  |  |  |
| C | Support Services |  |  |  |  |  |  |
| C1 | Training venue |  |  |  |  |  |  |
| C2 | Training food |  |  |  |  |  |  |
| C3 | Print and stationery |  |  |  |  |  |  |
| C4 |  |  |  |  |  |  |  |
| Sub Total |  |  |  |  |  |  |  |
|  | VAT (15%) |  |  |  |  |  |  |
| Grand Total |  |  |  |  |  |  |  |
| In Words |  |  |  |  |  |  |  |