Terms of Reference

Feasibility Study for a New Programme on Climate Resilient Livelihoods

by NETZ and its Partner Organisations

1. Background and rationale

NETZ Partnership for Development and Justice (NETZ) is a non-governmental charitable organisation registered in both Germany and Bangladesh. Since 1989, NETZ, in collaboration with its local partner organisations, has supported self-help initiatives in the areas of education, human rights, and climate resilient livelihoods.

Due to its geophysical conditions and socio-economic context, Bangladesh is widely recognised as one of the countries most vulnerable to the impacts of climate change. Natural disasters, climate related hazards and extreme weather events such as floods, droughts, heatwaves and cyclones have increased markedly in both frequency and intensity over recent decades. These developments have had far reaching adverse effects on agricultural production, food security, education, public health and housing.

At the same time, increasing pressure on natural resources is contributing to a rise in local conflicts, with serious implications for the human rights of marginalised communities. People living in extreme poverty are disproportionately affected, as they possess fewer assets and have more limited adaptive capacities. Effective and locally appropriate approaches to disaster risk reduction and climate adaptation remain insufficiently developed and implemented.

In response, NETZ and its partner organisations are developing a new programme aimed at addressing the impacts of climate change in highly affected regions, while also promoting climate protection measures. The programme seeks to sustainably reduce hunger and extreme poverty among households in remote floodplain areas, while addressing the structural marginalisation and vulnerability of indigenous communities and women in northern Bangladesh.

A central objective of the programme is to strengthen the capacities of these groups to cope with and adapt to climate related risks, while enabling them to effectively represent and safeguard the rights and interests of their families and communities.

2. Purpose, objectives and use

To establish a solid foundation for the conceptual development of the planned program, a feasibility study will be conducted. This study will evaluate the feasibility of the proposed intervention by analyzing its validity, alignment with the needs of the target groups, and consideration of all potential opportunities and risks. In addition, the study will evaluate the intervention against the OECD DAC criteria, namely relevance, coherence, efficiency, effectiveness, impact and sustainability

The primary users and beneficiaries of the feasibility study results are the local implementing organizations: MJSKS, Pollisree, and NETZ. They will use the findings and recommendations to refine and strengthen the programme design. The feasibility study will be submitted to the German Federal Ministry for Economic Cooperation and Development (BMZ) along with the program proposal.

3. Scope of work

3.1 Timeframe, geographic coverage

The feasibility study shall be conducted between 20 July 2026 and 17 August 2026. The study will cover the operational areas of the partner organisations, specifically in Lalmonirhat and Joypurhat districts in Bangladesh, where the respective partner NGOs are active.

3.2 Mandatory report structure and guiding questions

The feasibility study must follow the formal report structure provided below (see as well chapter 5 in this regard) and answer the mandatory guiding questions provided in Annex 1, which follow the key questions provided in the BMZ/bengo guidance note on procedures for feasibility studies and have been, where required, added and specified by NETZ. The consultants are free to include new sub-chapters under the chapter structure provided below, if feasible, to improve the overall structure of the report.

Mandatory report structure

| Chapter | Topic | Pages* | Remark |
| --- | --- | --- | --- |
|  | Cover page (including 1 picture from field level work) | 1 | This part is not counted towards the overall maximum length of 30 pages for the report. |
|  | Table of content | 1 |  |
|  | List of abbreviations | 1 |  |
| 1. | Executive summary | 1 |  |
| 2. | Purpose, objectives and utilisation of study | 2-3 | Mandatory guiding questions for these chapters will be provided to the selected consultant as Annex 1. |
| 3. | Context and problem analysis | 5-6 |  |
| 4. | Programme-executing organisations in Bangladesh and India | 2-3 |  |
| 5. | Target group and stakeholder analysis | 3-4 |  |
| 5.1 | Target group |  |  |
| 5.2 | Stakeholder |  |  |
| 6. | Assessment of the planned programme according to DAC criteria | 13-15 |  |
| 6.1 | Relevance |  |  |
| 6.2 | Coherence |  |  |
| 6.3 | Effectiveness |  |  |
| 6.4 | Efficiency |  |  |
| 6.5 | Significance / overarching development impact |  |  |
| 6.6 | Sustainability |  |  |
| 7. | Conclusion, incl. recommendations by the consultants | 2-3 |  |
|  | Annex (might include e.g. a) ToR of the feasibility study; b) profile of the consultants; c) evaluation matrix; d) final timetable of the study; e) list of conducted interviews and dialogue meetings; f) list of references and literature; g) questionnaires and other data/ information gathering instruments) |  | Annex not counted towards overall maximum length of 30 pages of the report. |

*Please note: The mentioned page numbers for the individual chapters are only rough suggestions. At the same time, they provide an indication how much focus/priority should be given to which topic.

3.3 Methodology

The methodology shall include at least the following:

- The consultant will review existing documents related to the programme to be evaluated, including the programme proposal.

- The consultant will review studies related to climate change and relevant evaluations and lessons learnt documents of previous NETZ supported programmes.

- The consultant will conduct interviews and/or focus group discussions (FGDs) with representative of the target groups and respective local communities, civil society, local authorities (i.e. government officials) and staff of partner organisations and NETZ.

- The consultant is expected to coordinate with the partner organisations and NETZ at the beginning of the feasibility study and continuously brief them as and when needed during the study. Debriefing session will be organised by the consultant with appropriate staff of the partner organisations at the end of each working area visit and with NETZ after the last working area visit to share and to discuss their findings and recommendations.

- A draft report by the consultant will be shared with all partner organisations and NETZ. Their feedback and suggestions will be reflected during the finalisation of the feasibility study report by the consultant.

A detailed working plan including methodology will be submitted by the consultant to NETZ for approval; for this purpose, NETZ will as well seek feedback and suggestions by the partner organisations.

4. Process

The following table summarises the different phases of the feasibility study and will be concretised in cooperation with the selected consultant.

| No. | Evaluation phases | Timeframe |
| --- | --- | --- |
| 1 | Planning meeting with staff members of NETZ in Dhaka | 20 July 2026 |
| 2 | Review of respective documents | 21 - 23 July 2026 |
| 3 | Field level work, including: a) Meetings with staff of partner organisations, b) data collection as well as c) dialogue meetings (incl. focus group discussions), interviews with representatives of the target group, local authorities, civil society etc. | 26 - 29 July 2026 |
| 4 | Preliminary dissemination of findings: a) de-briefing meetings with partner organisations’ staff in working areas and b) with NETZ staff members in Dhaka after field level works | a) during visit until 29 July 2026 and 02 August 2026 |
| 5 | Draft report preparation on the basis of mandatory report structure and guiding questions provided by NETZ and submission to NETZ for feedback | Until 09 August 2026 |
| 6 | Final report preparation, including feedback and suggestions of NETZ | By 13 August 2026 |
| 7 | Submission of final report | Until 17 August 2026 |

5. Outputs and deliverables

The consultant will prepare a report in English that presents the findings and addresses all guiding questions outlined in Annex 1. The report must adhere to the structure specified in Chapter 3.2 and have a maximum length of 30 pages (content only). Additional documents and case studies should be included in the report's annex.

6. Expert profile of the evaluation team

The evaluation team consists of one independent consultant with expertise in climate change adaptation and mitigation, particularly in relation to livelihoods, human rights, and gender issues. The consultant may hire an assistant as needed, including during field visits. The consultant is allocated 20 working days (including 2 travel days) to complete the assignment. Responsibilities include steering the feasibility study process, coordinating with NETZ and partner NGOs, compiling a draft report in English, and finalizing the report based on NETZ's feedback.

Required qualifications for the consultant:

- University degree in any discipline; priority given to Social Science/Agriculture Science.

- Professional experience in climate change adaptation, livelihoods, and human rights, including policy dialogue.

- Experience working with marginalized communities and advocacy.

- Willingness and ability to conduct required field visits.

- Excellent oral and written English skills.

Additional required qualifications:

- Proven track record in leading a study team.

- Proven experience in research, feasibility studies, situation analysis, baseline and evaluation surveys, and report writing.

7. Tentative timetable

The evaluation work consists of a total of 20 person-days, including 6 days for field visits, and will be conducted in 4 upazila in two districts, one district per partner organization. The consultant will commence work on 20 July 2026 and submit the draft report by 9 August 2026. The final feasibility study report will be submitted by 15 August 2026. Partner organizations will provide logistical support during field visits. The detailed schedule for the feasibility study will be finalized in cooperation with the selected consultant, based on the following template.

Template for detailed feasibility study schedule and quantity structure

| No. | Activity | Date | No. of days | Total person/days | Responsible person |
| --- | --- | --- | --- | --- | --- |
| 1 | Preliminary meeting and discussions | 20.07.2026 | .5 | .5 | NETZ staff |
| 2 | Planning, setting methodology and incorporating feedback of NETZ and partner organisations | 20-21.07.2026 | 1.5 | 1.5 | Consultant & NETZ |
| 3 | Review programme documents and secondary literature | 22 to 23.07.2026 | 2 | 2 | Consultant |
| 4 | Travelling to selected programme districts and back | 25.07.2026 and 30-07.2026 | 2 | 2 | Consultant |
| 5 | Field visit, interview, meetings with partner organisations, information collection, start writing process, prepare draft report | 26.07-29.07.2026 | 4 | 4 | Consultant |
| 6 | Discuss findings of the field research with NETZ Bangladesh Office in Dhaka | 01.08.26 | 1 | 1 | Consultant & NETZ |
| 7 | Compiling the first draft of the feasibility report by following the mandatory template provided by NETZ (see Annex I) | 02.08.26 to 09.08.26 | 5 | 5 | Consultant |
| 8 | Finalising the feasibility study report, adjust feedback of NETZ and partner organisations | 10.08.26 to 15.08.26 | 3 | 3 | Consultant |
| 9 | Presentation and discussion of findings with NETZ and partner organisations | 16.08.2026 | 1 | 1 | Consultant |
|  | Total |  | 20 | 20 |  |

8. Management of the evaluation

The following persons will be involved in the overall management of the feasibility study.

| Name (Position, NGO) | Responsibilities |
| --- | --- |
| Team Leader, CRL Team, NETZ | Overall coordination with the consultant and partner organisations; providing required programme documents to consultants; organisational support for consultants to plan working area visits with partner organisations; providing organisational feedback on draft report; all contract-related issues. |
| Project Directors of partner organisations | Coordination and planning of working area visit of consultants; ensuring participation of staff members and other stakeholders during programme area visits, interviews, dialogue meetings, debriefing etc.; providing organisational feedback on draft report. |

9. General conditions

- An individual financial contract will be signed with the selected consultant upon acceptance of these Terms of Reference (ToR).

- Given that the feasibility study involves direct interaction with target groups and partner organizations, NETZ expects a friendly, respectful, and gender-sensitive attitude and behavior throughout the study. The Code of Conduct and the Child Protection Policy, attached, are integral parts of the cooperation agreement with the consultant and their staff involved in the study.

- NETZ management reserves the right to reject any incomplete report, and as a result, may withhold the final installment of remuneration.

- NETZ reserves the right to amend this contract as needed for the program, with prior communication.

- The selected consultant will receive 25% of the total fee upon signing the contract. The final payment will be made after NETZ accepts the final report, ensuring it meets all required elements as outlined in the ToR.

- The contract may be terminated if the consultant fails to comply with the terms and conditions of the ToR.

- NETZ will cover food, accommodation, and transportation expenses based on actual costs, upon submission of receipts.

- NETZ and the partner organizations will hold the copyright for all results and documents produced during this feasibility study. Any publication, even in part, requires prior approval from NETZ.

- VAT and taxes will be deducted at source according to government regulations.

| Name, (NGO,) Position | Date | Signature |
| --- | --- | --- |