Terms of Reference (ToR)

For

Baseline Survey of the “Community-Based Child Protection Mechanism for the Children of Garment Workers in Bangladesh Phase II (CBCPM Plus)” Project

Terre des Hommes Netherlands (TdH NL) is seeking to contract for the Baseline Survey Consultant (s) of the “Community-Based Child Protection Mechanism for the Children of Garment Workers in Bangladesh Phase II (CBCPM Plus)” Project for the Bangladesh Country Office.

# Introduction to TdH NL

Terre des Hommes Netherlands (TdH NL) is an international non-governmental organisation (INGO) based in the Netherlands and registered with the NGO Affairs Bureau of the Government in Bangladesh that works to stop child exploitation. TdH NL is a member of the Terre des Hommes International Federation, a network of organisations working for the rights of children and to promote equitable development. To tackle child exploitation globally we support programming and advocacy to end child labour, the sexual exploitation of children, and child exploitation in humanitarian action. Please refer to the website: www.terre des hommes.nl. In Bangladesh, TdH NL works to prevent child exploitation in collaboration with the government, development partners, NGOs, and networks.

Our Vision

Children can flourish in a world free of all forms of exploitation.

Our Mission

Protect children by preventing and stopping child exploitation. And by empowering children to make their voices count.

# Project Background

# 2.1. Project Profile:

| Country(ies) | Bangladesh |
| --- | --- |
| Project Number and Title | BDSE00052025CBCPM: Community-Based Child Protection Mechanism for the Children of Garment Workers in Bangladesh Phase II (CBCPM Plus) |
| Total Budget (Euros) | 530,000 (Euro) |
| Donor(s) | Garcia Foundation |
| Project Duration | 3 years (36 Months) |
| Period Start Date: | 01 October 2025 |
| Project End Date: | 30 September 2028 |
| Thematic programme | SEC |
| Sub-programme (if any) | N/A |
| Location(s) | - Mirpur (ward 3, 5, 6), Dhaka North City Corporation, Dhaka - Kashimpur (ward 1, 2 & 3), Gazipur City Corporation, Gazipur |
| Lead and Implementing partner(s) | Lead Partner: TdHNL Bangladesh Country Office Implementing Partner: Breaking the Silence (BTS) |

# 2.2. Description / Background of the Project:

This project intends to address the child protection issues of the vulnerable children of Ready-Made Garment (RMG) workers living in a highly vulnerable situation in the slums around the RMG factories. They are easy prey for abuse and exploitation since the parents leave them alone or in the care of older siblings and neighbours in the slums. Many of these children are vulnerable to hazardous work, sexual exploitation, and violence.  Most of the children do not have access to education and protection services. The minimum wages earned by the RMG workers are inadequate to meet the living expenses of the family. Moreover, there are no early childhood development centers (ECD) and access to schooling is limited. The children do not have access to relevant government services in terms of child protection and development.

Under this project, community based child protection mechanisms have been functional with the engagement of the  child protection forum (CPF) members, child protection monitoring committees (CPMC), duty bearers, the parents, community leaders, relevant government officials, CSOs and the employers. Child protection mechanisms are playing a proactive role and conduct evidence-based advocacy with the relevant stakeholders including the government and employers to improve the conditions of the children of RMG workers and their families. RMG workers and the employers are oriented on child safeguarding, safety at the workplace and labour rights. The child-led forums will monitor, create evidence and initiate advocacy at the local and national levels. The project has also created access to ECD, mainstreaming children into public educational institutions, health care and support to the children vulnerable to exploitation and victims through linking access to service providers.

Project Results (Goals, Outcomes and Outputs):

Project Goal: Children of garment workers in Bangladesh in all of their diversity are better protected from sexual exploitation, and promote their rights by strengthening community-based response and support mechanisms.

Outcomes and Outputs:

| Outcomes | Outputs |
| --- | --- |
| Outcome 1: Children are empowered to prevent and respond to risks of online and offline sexual exploitation, and to advocate for and claim their rights. | Output 1.1: “Child Protection Forums (CPFs)” are initiated, and have knowledge, skills and confidence to identify and respond to risk of sexual exploitation and to lead community and institution based awareness and change initiatives. |
|  | Output 1.2: Children and youth have capability to monitor and report online and offline sexual exploitation, abuse and rights violation, and have access to public and private services. |
|  | Output 1.3: Early Childhood Development (ECD) centers for young children (4-6 years) are initiated with a gender-transformative approach and gender-sensitive teacher training, and children are mainstreamed in formal education. |
| Outcome 2: Families and communities are proactive and responsive to protect children from sexual exploitation, and to promote adequate care and support to the children to fulfill their immediate survival rights/basic needs. | Output 2.1: Families and communities are better aware of child protection and to identify and respond to cases of exploitation among children. |
|  | Output 2.2: Community protection committees and systems are strengthened to promote online and offline safety of diverse categories of children and youth, and actively engaged to address their basic needs. |
|  | Output 2.3: Sexual exploitation and abuse cases against children and youth are effectively monitored and followed up by the community protection committees, and refer the victims to the required support services. |
| Outcome 3: Government, CSOs, private sectors and other relevant stakeholders are responsive to strengthen the Child Protection System to address the needs of the children of RMG workers, and accountable to their obligations towards improved implementation of laws, policies, and systems. | Output 3.1: RMG workers and employers are trained on life skills, child safeguarding, occupational safety, labour rights and basic health and nutrition issues. |
|  | Output 3.2: Coordination and collaboration with government officials, duty bearers, service providers and CSOs are strengthened for specialised service provisions to children and youth of sexual exploitation, and effective implementation of relevant laws, policies and plans at all levels. |
|  | Output 3.3: Private sectors (e.g. employers, BGMEA and BKMEA, National Garment Workers Federation, Local and International Labour Organisations) are actively engaged to protect the rights of children and RMG workers. |

# Objectives of the Baseline Survey

The overall objective of the baseline study is to collect information and analyze it to synthesize a baseline report as per indicators set in a logical framework with the target groups in the working locations. The baseline study will gather concrete and specific data by developing the questionnaire following the indicators set in the project documents. However, at the end of the project cycle, an evaluation will be conducted to assess its impacts as part of project cycle management to measure the changes made through the project. The baseline study will serve as a reference point for the indicators in the project document.

Specifically, the baseline study will serve to:

- Establish a baseline data for project indicators. The baseline study will collect data that will be the starting point for change measurement, confirming baseline values for all outcome indicators.

- Provides an opportunity to refine indicators. The baseline study will help to refine indicators to track progress toward achieving desired outcomes. This may be through determining the extent to which certain indicators can be easily measured.

- Inform intervention phasing. The baseline study provides data that guides the phasing and targeting of project interventions.

Moreover, the baseline study will also serve to:

- To identify the current protection situation of children of garment workers and the barriers they face in receiving adequate care  and accessing their needs;

- To capture the existing knowledge, attitude and practices of targeted beneficiaries to address abuse and exploitation and the protection of children;

- To understand the perception of families and communities in providing adequate care  and support to their children and responding to their needs;

- To understand the perception of CSOs, Government, private sectors and other relevant stakeholders on abuse and exploitation, and responding to the needs for protection of the children of garment workers;

- To identify the potential private and public services with which the vulnerable children and victims of abuse and exploitation are connected/linked with and have accessing to relevant services;

- To understand the current situation of monitor and follow up the cases of violence against children and youth in the project areas and refer the victims to the required services;

- To capture the existing knowledge, understanding and practices of RMG workers and employers on occupational safety and labour rights; child safeguarding, and basic health and nutrition issues;

Key Indicators of the Project:

The objective of the survey is to collect data on the indicators of the intended goal, outcomes, and outputs of the project as set in the Result Framework, following the table.

| Project Results | Indicators |
| --- | --- |
| Goal: Children of garment workers in Bangladesh in all of their diversity are better protected from sexual exploitation, and promote their rights by strengthening community-based response and support mechanisms. |  |
| Outcome 1: Children are empowered to prevent and respond to risks of online and offline sexual exploitation, and to advocate for and claim their rights. | Percentage of children who demonstrate knowledge on child protection risks and behaviours and on what action to take to prevent it |
|  | Percentage of children who demonstrate self-confidence to identify and respond to risks to online and offline safety. |
|  | Percentage of children who took action against online or offline SEC threats |
|  | Percentage of children who participate meaningfully in decision-making processes. |
| Output 1.1: “Child Protection Forums (CPFs)” are initiated, and have knowledge, skills and confidence to identify and respond to risk of sexual exploitation and to lead community and institution based awareness and change initiatives. | Number of children trained to identify and respond to risks to online and offline safety |
|  | Number of children's networks (clubs, groups, movements etc) established and or strengthened |
|  | Number of children reached by awareness raising sessions and community engagement activities led by or co-created with children |
| Output 1.2: Children and youth have capability to monitor and report online and offline sexual exploitation, abuse and rights violation, and have access to public and private services. | Number of children trained in advocacy skills |
|  | Number of actions or initiatives taken by children through clubs/ committees/ networks to address their rights to protection and participation in decision making |
|  | Number of child peer educators trained to raise awareness on identifying SEC risks and reporting to promote safe and positive norms in peer groups and intergenerational spaces |
| Output 1.3: Early Childhood Development (ECD) centers for young children (4-6 years) are initiated with a gender-transformative approach and gender-sensitive teacher training, and children are mainstreamed in formal education. | Number of vulnerable children aged 4-6 supported and enrolled in preschool |
|  | Number of teachers trained on identifying and addressing specific needs of survivors of SEC including, in terms of education, child protection, safe play, psychosocial support, inclusion, safeguarding and confidentiality |
|  | Number of parents reached with information on the importance of their children's education |
| Outcome 2: Families and communities are proactive and responsive to protect children from sexual exploitation, and to promote adequate care and support to the children to fulfill their immediate survival rights/basic needs. | Percentage of family and community members demonstrating knowledge to identify and respond to risks of online and offline safety |
|  | Percentage of family and community members demonstrating positive attitude to prevent and respond to risks of online and offline safety |
|  | Number of child sexual exploitation cases identified and responded by community members. |
| Output 2.1: Families and communities are better aware of child protection and to identify and respond to cases of exploitation among children. | Number of parents/caregivers and community members reached through awareness raising to ensure children’s rights to protection, and identify and respond to sexual exploitation risks/cases |
|  | Number of parents/caregivers reached through positive parenting sessions. |
| Output 2.2: Community protection committees and systems are strengthened to promote online and offline safety of diverse categories of children and youth, and actively engaged to address their basic needs. | Number of local government and community-based child protection mechanisms trained on referral protocols and case management procedures. |
|  | Number of representatives from community-based child protection networks trained to prevent and respond to harmful social norms and practices. |
| Output 2.3: Sexual exploitation and abuse cases against children and youth are effectively monitored and followed up by the community protection committees, and refer the victims to the required support services. | Number of local government and community-based child protection officers local law enforcement trained on referral protocols and case management procedures. |
|  | Number of children at risk and survivors of sexual exploitation (and their families) who have received relevant social protection service packages. |
| Outcome 3: Government, CSOs, private sectors and other relevant stakeholders are responsive to strengthen the Child Protection System to address the needs of the children of RMG workers, and accountable to their obligations towards improved implementation of laws, policies, and systems. | Number of service providers with strengthened capacity to provide comprehensive and inclusive SEC service |
|  | Number of actions taken on SEC prevention and response that have been implemented by/together with private sector |
| Output 3.1: RMG workers and employers are trained on life skills, child safeguarding, occupational safety, labour rights and basic health and nutrition issues. | Number of employer representatives trained on gender, safeguarding, occupational safety, labour rights, basic health and nutrition issues of the RMG workers. |
|  | Number of RMG workers participated in the awareness raising on gender, safeguarding, occupational safety, labour rights, basic health and nutrition issues of the RMG workers. |
|  | Number of RMG workers linked with public and private institutions to access required services |
| Output 3.2: Coordination and collaboration with government officials, duty bearers, service providers and CSOs are strengthened for specialised service provisions to children and youth of sexual exploitation, and effective implementation of relevant laws, policies and plans at all levels. | Number of coordination initiatives to prevent and respond to harmful social norms and practices established between the community based child protection mechanisms and local government structures. |
|  | Number of national and sub-national coordination meetings held to establish and maintain referral mechanisms for preventing and responding to SEC. |
| Output 3.3: Private sectors (e.g. employers, BGMEA and BKMEA, National Garment Workers Federation, Local and International Labour Organisations) are actively engaged to protect the rights of children and RMG workers. | Number of participants from private sectors attending project awareness raising events (meeting/workshop/dialogue/etc.) |
|  | Number of local and national events/ activities (meetings, workshops, webinars) were conducted with diverse stakeholders. |

Note: The consultant/firm will strictly follow all the output, outcome and goal level indicators mentioned in the Result Framework of this project.

# Methodology approach

A suitable and detailed methodology in line with the objectives of the baseline should be provided by the consultant at the inception. This should include a mixed method approach, integrating quantitative and qualitative methods to achieve the final objectives, and provide details of sampling units (individuals including children, household, group, private sector players’, government stakeholders etc.). The consultant/firm will use different methods such as desk review, observation, survey, key informant interviews (KIIs), in-depth interview (IDI), focus group discussion (FGD) with different stakeholders to collect data from the community and institutions level. Besides, the consultant/firm will do case/success stories. The consultant/firm is expected to propose appropriate methodology with the required number of nationally representative samples for the quantitative part maintaining standard statistical formula. For the qualitative survey, the consultant/firm must consider the survey prerequisites, individual verbatim for triangulation. However, all data collection methodologies and determination of sample size should be considered in line with the discussion and agreement between the survey team, TdH NL and partner organisations. It is expected that all methods will be conducted by taking into consideration child safeguarding and ethical standards regarding the gathering of data from all relevant stakeholders.

The consultant will develop a comprehensive study methodology that will be reviewed by the TdH NL team during an inception phase.

In MEAL processes TdH NL encourages the participation of local stakeholders, including partners, community members, youth and where feasible, children. It is required that the Inception Report and survey design should include adequate details of how local stakeholders groups, including partners, community members, youth and/or children, will be incorporated in ways that are responsible and ensure the safety of participants. The project team will organise introductions with stakeholders and assist in mobilising participation and the provision of feedback to participating communities.

# Baseline Study Scope

The focus of this study will be restricted to the project outcome indicators as contained in the project logical framework. It shall be conducted among the targeted communities that includes:

| Types of beneficiaries/stakeholders | Beneficiary/ stakeholders to be covered under this survey | Types of beneficiaries/ stakeholders |
| --- | --- | --- |
| Members of Child Protection Forum | 90 | Direct |
| Members of Children Groups | 750 | Direct |
| Members of Youth Innovation Labs (YIL) | 15 | Direct |
| Children (4-6) of Early Childhood Development (ECD) | 1500 | Direct |
| Children receives referral and linkages support on child protection issues | 300 | Direct |
| Families and Communities through positive parenting, and awareness sessions | 12,500 | Direct=2,500 Indirect=10,000 |
| Members of child protection monitoring committee | 75 | Direct |
| RMG workers (18-45) through orientation/awareness sessions | 500 | Direct |
| RMG workers to access health care and psycho-social services | 350 | Direct |
| Staff of factories including KAC and Mark Designer Fashion Ltd. of Garcia Foundation | 200 | Direct |
| Government officials, duty bearers, service providing agencies, relevant ministries and departments | 100 | Indirect |
| Local government institutions and representatives | 20 | Indirect |
| Members of National Garment Workers Federation, BGMEA, BKMEA and International Labour Organisation | 20 | Indirect |
| CSOs including media, local and national NGOs and educational institutions | 150 | Indirect |
| Members of Community Based Child Protection Committees (CBCPC) and Child Welfare Board (CWB) | 100 | Indirect |

Note: The consultant/consultancy firm will be requested to take appropriate sampling from the above mentioned beneficiaries.

The entire study should be delivered within a maximum of 40 working days including planning, data collection and analysis as well as submission of final report and other deliverables related to the task. This study will be conducted in the following geographic locations:

| Districts | Upazila/Police Station (Sub-districts) | Union/Ward |
| --- | --- | --- |
| Dhaka | Mirpur | Ward No. 3, 5 & 6, Dhaka North City Corporation |
| Gazipur | Kashimpur | Ward No. 1, 2 & 3 Gazipur City Corporation |

Besides, the following Scope and Focus of the consultancy work will be considered under this assignment:

- Conduct an inception meeting for the assignment and prepare an inception report with detailed methodology (both quantitative and qualitative), timeline, team plan, and draft data collection tools (including consent and assent form), analysis plan, training plan for enumerators, sampling plan, child-safeguarding plan, budget plan and outline of the final report;

- Collect and review of existing project documents, such as result framework and other related documents from TdH NL as a part of desk review process;

- Design the survey in consultation with TdH NL and partners in inception meeting;

- Based on the comments received by TdH NL on the inception report, revise the study design, methods or tools accordingly.

- Define a detailed approach and methodology for gathering and analysing data:

- Develop data collection tools, pre-test, and finalise in consultation with the project personnel;

- Prepare the survey manual, fieldwork protocols according to agreed methodologies;

- Conduct training of the data enumerators and supervisors;

- Collect data including cleaning, validation, and entry;

- Develop data analysis and management plan;

- Data analysis.

- Prepare draft report and share with TdH NL and implementing partners for feedback;

- Incorporate the feedback received from the project personnel and project partners;

- Give a presentation to TdH NL management on the final draft Report;

- Finalise and submit the final evaluation report and the collected raw data to TdH NL.

Note: The following tasks for the consultant will need to focus on the above-mentioned aspects, however, are not limited to them. Other associated tasks and subtasks may and should be undertaken based on discussion and need.

# Stakeholders to be involved in the Final Evaluation process

Beneficiaries and the project's key stakeholders will be involved in this study process by participating as respondents and discussing providing authentic data and information to the survey team, along with the following stakeholders. The key stakeholders and beneficiaries will be selected based on the appropriate methodology proposed by the consultant/firm after the selection process, and they need to follow the principles of gender and inclusion of marginalized groups.

| Stakeholder Name | Main roles in the Final Evaluation study |
| --- | --- |
| Project Team | TdH NL Bangladesh country office teams (project and MEAL) will: - Develop ToR - Recruit the consultant(s) - Provide the consultants with templates of the Inception Report and Final Baseline Report. - Provide the consultant with relevant documents such as the project proposal, log frame, and other related documents. - Produce mission letters if required. - Coordinate with partners for field data collection. - Coordinate and work with NGO partners and Global Teams to review the Inception Report, survey Report, and Slide presentation. - Will provide guidance and orientation on child safeguarding and ethics, project background, and context. - Coordinate the assessment of the quality of the consultancy service deliveries. |
| MEAL Team | The Global Teams, including MEAL, PDQ, REI, and/ or Programme, will: - Involved in the recruitment of the consultant if needed - Provide relevant technical support - Review and approve the ToR - Review and approve the Inception Report and relevant data collection tools - Review and approve the survey Report |
| Consultant (s) | The consultant/firm will follow the ToR to conduct a Baseline Survey and ensure deliverables are as expected in those working areas, following the indicators set and synthesis of specific data and report as stated: - Develop an inception report following the template provided by TdH NL, including data collection tools and a work plan - Develop a data analysis plan as mentioned in the inception report template. - Recruit qualified data collection teams and provide training to them. - Translate data collection tools into the local language(s) and conduct field tests. - Carry out quantitative and qualitative data collection and ensure the quality of the collected data. - Carry out data processing, including data cleaning. - Develop data entry tools/ online data collection tools, - Analyse data based on the disaggregation of each indicator in the provided log frame. - Provide a preliminary finding presentation to the TdH NL for feedback. - Produce a draft report based on the provided template. - Produce the final baseline study following the TdH NL format by addressing all comments from TdH NL. - Develop a comprehensive slide presentation of the baseline study and provide a presentation in the dissemination workshop. - All reports, data collection tools, and slide presentations are required to be submitted to TdH NL for review and approval. The consultant is responsible for addressing all the comments and submitting them back for final review and approval. |
| Partners | - Partners are to extend all field support to conduct the survey, with the selection of target groups and organize FGD and KII as relevant to complete the baseline study in the working locations, and provide inputs to the data collection tools and evaluation report. |

# Timeline and Deliverables

The consultancy will be completed from 20 May to 30 June 2026. The consultant/consultancy firm will be expected to complete all the related tasks and final report submission of the survey within this timeframe. In accordance with the timetable, the evaluator(s) will produce and/or provide to TdH NL the following:

| # | Deliverables | Deadline |
| --- | --- | --- |
| 1 | Participate in the inception meeting to present and discuss project details, the goal of the baseline study and to receive from the project team the required information and documents needed to perform the survey. | 1st week |
| 2 | Inception report including the study design, work plan, final data collection tools in English and local language, methodology, and data analysis plan (template of the report will be provided) | 2nd week |
| 3 | Gain ethical approval or any other approval needed to collect data (as required based on data and context) | 3rd week |
| 4 | Training materials for data collectors, including data collection and quality assurance mechanisms/instruction/guidelines/ protocol. | 3rd week |
| 5 | Online data collection forms in KOBO or other effective mobile data collection applications, if used. | 4th week |
| 6 | Field report after completion of the data collection. | 5th week |
| 7 | Participate in a reflection workshop with TdH NL staff and partners to present and discuss findings. | 6th week |
| 8 | Final completed baseline study report in English addressing all comments/feedback from TdH NL and/or partners (template of the report will be provided) | 7th week |
| 9 | Child-friendly version baseline report in English addressing all comments/feedback from TdH NL and/ partners | 7th week |
| 10 | Final comprehensive slide presentation of the baseline study results. | 7th week |
| 11 | Raw data: - All completed questionnaires and consent forms (if hard copies are used). - Raw quantitative/ qualitative data (transcript, data entry in Excel, English translation) - Final clean data used for data analysis. - Final data analysis outputs (in table, graph…) used for the report and slide presentation (including data analysis by indicator) | 7th week |

TdH NL will oversee the process and maintain responsibility for accountability and guidance throughout all phases of execution, and approval of all deliverables.

# Management and supervision

The consultant will report directly to the Country Manager or other assigned member of TdH NL staff and work closely with the Advisor-PME & Fundraising and Project Coordinator-CBCPM Project, along with others.

Nazrul Islam

Country Manager Bangladesh

n.islam@tdh.nl

Mohammad Nurul Kabir

Advisor-PME & Fundraising

m.nurulkabir@tdh.nl

The consultant is expected to use the TdH NL study report templates that include The study Report template and Inception Report template and can be requested through m.nurulkabir@tdh.nl or m.sumon@tdh.nl

The TdH NL Country Office will provide preparatory and logistical assistance to the Consultant, including:

- Background materials (project proposal, quarterly report data, Logframe, etc.)

- Meetings, phone/ email communication with relevant TdH NL staff

- Identify interviewees and provide contact information

- Logistical support for the field visits

- Arranging meetings and appointments with stakeholders and beneficiaries in project sites (if necessary)

# Child Safeguarding Measures

The consultant must adhere to the TdH NL Safeguarding Policy, therefore as a condition of entering into a consultancy agreement the individual/firm must:

- Read and Sign the TdH NL Safeguarding Policy and abide by the terms and conditions therein.

- Read and Sign the TdH NL Code of Conduct

Additionally (as also be stated in the contract):

- It is the responsibility of the consultant or consultancy firm to safely recruit, train and manage any subcontractors (such as researchers, enumerators, translators, etc.) in relation to safeguarding.

- Safeguarding of subcontracted staff during the baseline study is the responsibility of the consultant.

- The consultant is responsible of conducting a safeguarding training (using the Safeguarding and Ethical Evaluation presentation) for any subcontracted staff

Any violation /deviation of complying with TdH NL’s said policy will result in termination of the agreement.

# Ethical Considerations and Conflict of Interest

The consultant must ensure that no one is forced to provide information. The Baseline study objectives will be clearly explained to all respondents before collecting data, with written consent and/or assent forms signed by respondents or guardians. The consultant must commit to maintaining confidentiality and unbiased data collection.

# Quality assessment of the evaluation report will be based on:

The quality of the study process and outputs will be assessed based on:

- Design and methodology

- Analysis of findings based on facts and data for reliability

- Structure and clarity of the report

# Selection criteria of the applicants for the interview

Expression of Interest, including a technical and financial proposal for the evaluation study, will be requested through open bidding. The consultant/consulting firm for the assignment will be primarily selected based on the relevant experience of the consultant and technical and financial proposals, which will be compared among the applicants.

- Quality of baseline proposal

- Experience and knowledge of the consultant

- Schedule

- Budget

Shortlisted proposals/applicants will be subject to an interview, including a presentation of their proposal, clarifying questions on the proposal, and validation of information. The final selection will be made based on the interview and by the project. The technical proposal will carry 35% marks for the relevant experience of the consultant, 50% marks for adequacy of methodology and work plan, and 15% marks for the financial proposal during the proposal assessment.

# Budget

The consultant will include a financial proposal that outlines a detailed breakdown of all costs required to complete the baseline study.

- Payment Schedule

- 40% on submission of inception report (with work plan, data collection tools)

- 30% on submission of 1st draft of the baseline report

- 30% on submission of approved final report and slides of findings

The consultant/consulting firm is expected to provide deliverables within the stipulated period as well as submit the final report, maintaining the quality. If, for any reason, the consultant/consulting firm fails to deliver services within the stipulated time, the consultant/consulting firm needs to inform TdH NL in time with a valid and acceptable explanation. Failing to do this may result in a late payment on time. Please note that all VAT and tax amounts will be deducted from the total amount at the source (i.e., TdH NL) as per government regulations.

# Skills, Competencies, Experience and requirements

The consultant (s) engaged to undertake the assignment must fulfil the following requirements: (qualification and skill areas, technical competence, language proficiency, and in-country or regional work experience, process management skills):

- Minimum 10 years experience in performing survey/ assessment/ review/ evaluation and sound understanding of survey concepts, methodologies, and tools;

- The lead consultant and the relevant members of the team should have an excellent research background and have proven track record in conducting a similar type of assignment;

- Knowledge and experiences on child protection, child labour, child abuse and exploitation, skill training, child rights, right-based approach and gender, and working with RMG workers and employers will be given preference;

- Ability to work collaboratively with multiple individuals, groups and team;

- Demonstrable expertise in both quantitative and qualitative data analysis;

- Excellent data interpretation and report writing skills with high quality English;

- High professional level of writing reports and using advanced statistical analysis programs such as SPSS, Stata, Kobo, etc.

- Experience in providing training to data collection teams.

- Evidence of having undertaken similar assignments.

- How to apply

# Application process and timeline

TdH NL Bangladesh Country Office invites interested individuals and agencies to submit the following application documents:

- Technical proposal outlining their motivation for the application, the methodological approach and the resources required (documents, survey questions, FGD and KII checklists, etc).

- A proposed activity schedule/work plan with a time frame.

- CVs of the lead consultant and the team members.

- Two recent reports that were written by the Lead Consultant.

- Financial proposal detailing evaluators' itemised fees, data collection and administrative costs.

Interested individuals/organizations are requested to submit the proposal with the above-mentioned documents to bangladesh@tdh.nl on or before 15th May 2026 by 5:00 PM with “EoI on Baseline Study of CBCPM Plus Project” as the subject line. Different files, i.e., technical, financial, and a cover letter, need to be attached to the email in the name of each file. The proposals (both financial and technical), including CVs, are requested to be submitted in PDF format.

Budget: The total budget for the baseline study will be a maximum of BDT 500,000, inclusive of all applicable VAT and taxes

Our Commitment to Diversity, Integrity and Child Safeguarding

We are not looking for just one type of person - we want to recruit people who can add fresh perspectives, innovative ideas and challenge our thinking. We are especially interested in people whose lived experiences help us to see things we might otherwise miss, and enable us to do better work with and for children. Whether or not you meet 100% of the criteria, we want to hear from you, because we know that different voices, ideas, perspectives and knowledge, working together will enable us to better the lives of children around the world.

TdH NL is committed to ensuring diversity and gender equality within our organisation. We continue to learn about intersectional considerations and power distribution within our organisation and our work. We are dedicated to preventing and eradicating any type of misconduct including sexual harassment, exploitation and abuse, any other type of misuse of power, lack of integrity or financial misconduct.

Note: We place a high priority on ensuring that only those who share and demonstrate our values are recruited to work for us, this includes a commitment to diversity and inclusion at all levels of our work. All offers of employment will therefore be subject to satisfactory references and appropriate screening checks, which include a valid criminal record check, terrorism finance checks, and/or integrity screenings/references relating to misconduct and disciplinary actions in prior employment.

TdH NL is particularly committed to keeping children and vulnerable individuals safe, and has zero tolerance on (child) abuse. Every TdH NL employee is bound by the TdH NL Code of Conduct that describes the expected behaviour by staff, in particular with regards to Safeguarding children and (young) adults in our programmes. Child safeguarding measures are part of our selection and recruitment process. By submitting your application you accept that TdH NL will conduct such pre-employment screening for successful candidates. TdH NL participates in the Inter-Agency Misconduct Disclosure Scheme.