## OPS (hidden)
2018 Procurement Plan
SL | Description of the Goods / Services | Quantity | Value per unit (in USD) | Expected value, USD | Expected date of completion | Remarks | Sector | Additional comments | Category | Status | Updated Comments
1 | International procurement of medicines and supplies | specification attached |  | 600000 | ASAP |  | Health | Health confirmed that this covers the needs for entire 2018 (in combination with Dec 2017 order that is in the pipeline) including for contingency, as part of stock could be lost during monsoon season
2 | Local procurment of medicines | specification attached |  | 100000 | ASAP |  | Health | Authorization from HQ PH to be sought by Health
3 | HIS toolkit and other printing |  |  | 10000 |  |  | Health |  | Not in OL
4 | Stretcher | 200 |  | 220000 | ASAP | picture attached, price to be determined | Health |  | Not in OL
| 2 PHCs in Nayapara |  | 25000 | 50000 |  | Planned PHC in Chakmakul/Kerountuli is 1 of 10 agreed with MoH - not to be under Health but peaceful coexistence; | Health |  | Not in OL
| Relocation of Health structures to be included (Health clinic by MTI + RI - definitely in areas which will be flooded); |  |  |  |  | Input needed from Health sector; Programme and Supply to review and quantify | Health | Only health posts are relocation; TLC, Community Centers, CFS and other temporary structures to be abandoned. Once we have Frame Agreement, we should build modular structures | not in OL
| Nutritional tems (medicines) |  |  | 15000 |  | In addition to nutrition items ordered in Dec 2017 | Nutrition |  | Not in OL
| Nutrition items (plumping nut) | [6 empty] | Health to review the needs based on the input from Supply (pipeline) | Not in OL
| Shelter ID | 210000 | 0.11 | 23100 | 20/01/2018 - 24/01/2018 | To support UNHCR's initiative in creating address mechanism in camps and settlement | IM
| Tablet | 50 | 180 | 9000 | 31/01/2018 - 31/03/2018 | The devices are requested to support the roll-out of e-Mapping of all sites by UNHCR | IM
| Waterproof Drone | 3 | 2000 | 6000 | 31/01/2018 - 31/03/2018 | To allow staff to collect and analysis information during the raining season | IM
| Mobile phones for the data collection process | 300 | 136.147 | 40844.1116 | regularly in 2018 | • Health Survey (Each 3 Month) • REACH Site Profiling Survey (Every Month) • Shelter Assessment (Every 3 Months) • Key informant Survey (Every 2 months) • Need Assessment | IM
| Laptops | 20 | 1351 | 27020 | 01-28 Feb 2018 | Individual Exercise Procurement Plan - under the assumption that permission is granted to UNHCR by the Government in February 2018 | Registration | HQ | ICT | Received
| Webcam Logitech C525 (compatible with proGres) | 0 | 40 | 0 | 01-28 Feb 2018 |  | Registration | Done - Delivered in COX | ICT | Received
| DactyScan84c Finger print scanners | 0 | 572 | 0 | 01-28 Feb 2018 |  | Registration | Done - Delivered in COX | ICT | Received
| Iris Scanners IrisShield BK2121U (compatible with proGres) | 0 | 550 | 0 | 01-28 Feb 2018 |  | Registration | Done - Delivered in COX | ICT | Received
| proGres Server (laptop server) - P51 (higher specs) | 2 | 3500 | 7000 | 01-28 Feb 2018 |  | Registration | HQ procurement | ICT | Pending
| BIM server (laptop server) - P51 (higher specs) | 8 | 3500 | 28000 | 01-28 Feb 2018 |  | Registration | HQ procurement | ICT | Pending
| Internal HDD for BIMS laptops (Samsung 960 EVO M.2 NVMe SSD 500GB) | 2 | 260 | 520 | 01-28 Feb 2018 |  | Registration | Done - Delivered in Bangkok | ICT | Received
| Additional memory for BIMS laptops (SO DDR4 16GB PC19200 (2400)) | 16 | 200 | 3200 | 01-28 Feb 2018 |  | Registration | Done - Delivered in Bangkok | ICT | Received
| External HDD - Samsung Portable SSD T5 1TB (Backup - BIMS / proGres) | 1 | 450 | 450 | 01-28 Feb 2018 |  | Registration | Done - Delivered in Bangkok | ICT | Received
|  | 0 |  | 0 |  |  |  |  | ICT
| External hard disk (3TB (Seagate or WD) | 8 | 200 | 1600 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Rub hall | 10 | 25000 | 250000 | 01-28 Feb 2018 |  | Registration | HQ procurement | Other | Received
| Foldable plastic chairs for waiting area | 1000 | 12 | 12000 | 01-28 Feb 2018 |  | Registration | Local procurement | Furniture | Received
| Foldable plastic tables | 300 | 30 | 9000 | 01-28 Feb 2018 |  | Registration | Local procurement | Furniture | Received
| Wooden benches | 100 | 30 | 3000 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Received
| Plastic sheets for flooring (for 10 sites, rolls of 10m by 100m) | 20 | 500 | 10000 | 01-28 Feb 2018 |  | Registration | Local procurement | Furniture | Received | Outside the UNHCR rub-hall, ready to be moved to site.
| Generator fuel (appx 1000 litres) | 1000 | 1.5 | 1500 | 01-28 Feb 2018 |  | Registration | Local procurement | Fuel | Pending | To be procured in smaller quantities during verification (through admin/field)
| Electrical extension cables/multi sockets | 100 | 4 | 400 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| Electrical extension reels/cords (at least 50m) | 10 | 50 | 500 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| Stand Fans | 100 | 20 | #VALUE! | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| Portable evaporative air coolers | 15 | 200 | 3000 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| Secure paper - in reams | 170000 | 0.15 | 25500 | 01-28 Feb 2018 |  | Registration | HQ procurement | Stationery | Partly received | First batch of 150,000 papers delivered on 21/05. The remaining will be delivered in June
| Toner (for colour printer; sets of 4) | 80 | 200 | 16000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Toner (for black and white printer) | 80 | 100 | 8000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Visibility T-shirts for registration staff | 300 | 10 | 3000 | 01-28 Feb 2018 |  | Registration | Local procurement | Visiblity | Pending | To be printed by TAI with three Govt, UNHCR, TAI logos. Awaiting the conclusion of discussions.
| Post it (serie de 12) | 200 | 2 | 400 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Posters and leaflets | 10000 | 4 | 40000 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Pending | Awaiting conclusion of discussions with the Govt. Would be clear after 24 May
| Radio advertisement slots (lumpsum) | 20000 | 1 | 20000 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending | Awaiting conclusion of discussions with the Govt. Would be clear after 24 May
| Electrician (contractor wages) | 10 | 1000 | 10000 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending | To be recruited under TAI from the refugee community, using resources utilized by the Field teams.
| Runners (refugee volunteer) / Interpreter | 110 | 1125 | 123750 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending | To be recruited under TAI from the refugee community, once the exercise starts
| Training venue and refreshments (lumpsum) | 5 | 3750 | 18750 | 01-28 Feb 2018 |  | Registration | Local procurement | Conference service | Partly received | Parts of the training have been conducted, some on-going. At least one more is planned.
| Visibility thin vest for volunteers and runners | 500 | 10 | 5000 | 01-28 Feb 2018 |  | Registration | Local procurement | Visiblity | Pending | To be printed by TAI with three Govt, UNHCR, TAI logos. Awaiting the conclusion of discussions on 24 May
| Mini vans (daily rent for 90 days) | 4 | 4500 | 18000 | 01-28 Feb 2018 |  | Registration | Local procurement | transport | Pending | To be procured under TAI
| Bus (daily rent for 90 days) | 10 | 9000 | 90000 | 01-28 Feb 2018 |  | Registration | Local procurement | transport | Pending | To be procured under TAI
| Raincoat, umbrella, boots (for 300 people) | 300 | 50 | 15000 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending
| Bottled water, biscuits, apple, cake (daily provisions, lumpsum) | 50000 | 1 | 50000 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending | To be procured under TAI
| UV Ink (bottles) | 100 | 7.8 | 780 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| UV Lamps | 10 | 6 | 60 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| USB Hub 3.0 | 200 | 17 | 3400 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Ration Card UNHCR | 50000 | 0.05 | 2500 | 01-28 Feb 2018 |  | Registration | HQ | Stationery | Received
| Puncher ROUND | 50 | 3 | 150 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Puncher HEART | 50 | 3 | 150 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Megaphone (Standard, Item) | 50 | 3 | 150 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| AA Dry Cells (A box of 12, Sets) | 10 | 12 | 120 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| Cleaning fluid (Alcohol cleaning/toner, Bottle) | 100 | 2 | 200 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Cotton wool (Uncut (not in pellets), Bundle) | 50 | 5 | 250 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Received
| Printing Paper (Carton of 4 reams (2,000 papers), Item) | 100 | 15 | 1500 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Arch Lever Files (Kent, Box) | 350 | 3 | 1050 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Pens (Box of 24, Box) | 20 | 5 | 100 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Staplers & staples (Small size, Package) | 60 | 5 | 300 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Paper punchers (Big size, Item) | 10 | 10 | 100 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Electric blower (hoover) (Hand held, Item) | 8 | 50 | 400 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| A4 Laminating pouches (Ream of 500, Ream) | 20 | 30 | 600 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Removed
| Plastic folder (A 4 Size ream of 100 for refugee document (photo slip ), Ream) | 1000 | 20 | 20000 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | in process | Most quantities received
| Laminator Machine (For A4 Laminates, Item) | 6 | 60 | 360 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Water Dispenser (Local procuremently available, Item) | 10 | 180 | 1800 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending
| Marker pens (Thin balled with indellible ink, Item) | 120 | 4 | 480 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Note pad (Small, Piece) | 200 | 0.5 | 100 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Flourescence Tube (Round tube , Piece) | 100 | 3 | 300 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| Highlighters (Different colours (carton), Carton) | 5 | 10 | 50 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Maker Pens (Normal, Box of 6) | 5 | 15 | 75 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Flipchart plain paper pad (25 by 30.5 inches 40 sheets pad (various colors), Pads) | 10 | 8 | 80 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Masking tape (Large, Piece) | 6 | 1 | 6 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Yellow stickers (Normal, Box) | 10 | 5 | 50 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Stapler Remover (Typical (any brand), Piece) | 30 | 1 | 30 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Stamp Pads (Blue, Piece) | 70 | 1 | 70 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Stamp Pad ink refill (Blue, Piece) | 20 | 2 | 40 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Flipchart and Tripod (Light Magnetic Whiteboard/flipchart, Piece) | 7 | 100 | 700 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| LCD Screen cleaner spray (Bottle of 100ml, Item) | 25 | 10 | 250 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| Clipboards (Plastic, Item) | 30 | 2 | 60 | 01-28 Feb 2018 |  | Registration | Local procurement | Stationery | Received
| PVC White cloth (White soft plastic 1m by 15m, cf advertisers' poster materials , Rolls) | 16 | 30 | 480 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Received
| Latex gloves (Disposable hand gloves. Pack of 100, Box) | 50 | 15 | 750 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Pending
| D Batteries (Pack of 12 Energizer for megaphones, Packets) | 50 | 15 | 750 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received
| RJ 45 (Pack of 100, Packets) | 15 | 5 | 75 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Antiseptic liquid (Rinse free hand sanitizer, Bottle) | 50 | 2 | 100 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Received
| Sisal rope (Basic (white), Rolls) | 30 | 2 | 60 | 01-28 Feb 2018 |  | Registration | Local procurement | Other | Received
| Barcode Labels (Adhesive, direct thermal, roll of 1,000) | 0 | 15 | 0 | 01-28 Feb 2018 |  | Registration | Cancel | ICT | Cancelled
| Printer for Barcode Label (Zebra or other brand) | 0 | 400 | 0 | 01-28 Feb 2018 |  | Registration | Cancel | ICT | Cancelled
| Desktop computer (HP Elite 8300) | 5 | 600 | 3000 | 01-28 Feb 2018 |  | Registration | Done - Delivered in CXB | ICT | Received
| Printers (black and White) (HP LaserJet Enterprise M600 M602N (with wireless capability) | 6 | 500 | 3000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Uninterupted Power Supply (UPS) (APC Smart 1500) | 14 | 570 | 7980 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Pending
| Network switches (Cisco 24 port GB) | 10 | 300 | 3000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | 8 received, 2 pending
| Generators (FG Wilson =>10kVA enclosed soundproof) | 4 | 3500 | 14000 | 01-28 Feb 2018 |  | Registration | Local procurement | Electric | Received | In parking lot, waiting to be moved
| Portable photocopier (Canon ImageClass D550 ) | 4 | 900 | 3600 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| WIFI/ Wireless router (Aruba/ubiquiti) | 6 | 500 | 3000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Pending
| Mikrotik Router RB850Gx2 | 2 | 200 | 400 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| LAN Patch Cord CAT6 (3m) | 40 | 6 | 240 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | 15 received, 25 pending
| LAN tester | 2 | 45 | 90 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Cable ties small | 500 | 1 | 500 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Cable ties medium | 500 | 2 | 1000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Cable ties long | 500 | 3 | 1500 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Electric tape | 20 | 0.5 | 10 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Rack 24U | 2 | 300 | 600 |  |  | Registration | Local procurement |  | Pending
| Ethernet Network Cables (Linet 35 (carton) | 4 | 125 | 500 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | 2 received, 2 pending
| Network Toolkit (Standard with crimpers, network testers, pliers enclosed in case) | 4 | 60 | 240 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Pending
| Barcode readers (USB Honeywell (USB Hand held)) | 20 | 100 | 2000 | 01-28 Feb 2018 |  | Registration | HQ |  | Received
| Printers (Colored) (Color Laserjet Pro MFP M277dw) | 4 | 400 | 1600 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Tripod stands (For cameras. 70 inch basic stand) | 70 | 40 | 2800 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Laptop Cooling Pads (Deep Cool, Thermaltake or any good brand) | 120 | 30 | 3600 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| Fast Scanner | 20 | 500 | 10000 | 01-28 Feb 2018 |  | Registration | Local procurement | ICT | Received
| SGBV training UNHCR staff (1 day/25 pers) | 2 |  | 2000 | March | Outside of the office; no overnight, refreshment, lunch and venue only; | SGBV
| SGBV ToT UNHCR and partner staff (5 days / 25 pers) | 1 |  | 3000 | February/March | Outside of the office; no overnight, refreshment, lunch and venue only; | SGBV
| SGBV training (1 day / 20 pers) | 4 |  | 4000 | quarterly | Outside of the office; no overnight, refreshment, lunch and venue only; | SGBV
| Translations- IEC material and documents for PSEA &SGBV | 6 |  | 2000 | February |  | SGBV
| Designing of IEC material (Leaflets / posters) for PSEA &SGBV | 6 |  | 1500 | March |  | SGBV
| Printing of IEC material (Leaflets / posters) for PSEA &SGBV | 6 |  | 3000 | March |  | SGBV
| Female Sanitary Hygiene kits for reproductive age-group | 200000 |  | 1000000 | Entire year |  | SGBV | Price to be determined by Supply
| CiCs office support | [5 empty] | Site Management
| Portable projectors | 10 | 370 | 3700 | 2018-01-30 | Easy, handy to carry and project at field | Site Management
| Laptop | 10 | 450 | 4500 | 2018-01-30 |  | Site Management
| White boards set | 10 | 120 | 1200 | 2018-01-30 | White board along with duster and board marker | Site Management
| Printer | 10 | 450 | 4500 | 2018-01-30 | Portable printer easy to print at field level with minimum electricity requirement | Site Management
| Printer Cartridges | 20 | 20 | 400 | 2018-01-30 |  | Site Management
| Solar panel (invertor, battery and solar panel) | 10 | 950 | 9500 | 2018-01-30 | to support back up for laptop and printer; | Site Management
| Multi chords | 20 | 10 | 200 | 2018-01-30 |  | Site Management
| Desk and chair | 10 | 150 | 1500 | 2018-01-30 | office level desk | Site Management
| Chairs | 40 | 20 | 800 | 2018-01-30 | office level normal chairs for visitors | Site Management
| Stationery package | 10 | 50 | 500 | 2018-01-30 | Pens, scissor, tape, flipchart, marker, flipchart stand, notebook | Site Management
| Rubber boot | 10 | 50 | 500 | 2018-01-30 | for rainy season of different size | Site Management
| Raincoat | 10 | 30 | 300 | 2018-01-30 | for rainy season of different size | Site Management
| Caps/hats | 10 | 20 | 200 | 2018-01-30 | for summer season of different size | Site Management
| GPS Garmin | 5 | 210 | 1050 | 2018-01-30 | CiCs of the camps under UNHCR management | Site Management
| Smartphone | 10 | 190 | 1900 | 2018-01-30 | able to collect data by different android applications | Site Management
| CIC Structures |  |  | 1600000 | 1905-07-10 | CIC structures (20) including meeting rooms and dormitories | Site Management | 7 Feb: Negotiations on the PPA ongoing; this might be included in the partnership agreement
| 24 Site Management Trainings Part 1- 2 days- 22 participants | 1 |  | 3200 |  |  |  | Price to be determined by Supply
| 24 Site Management Training Part 2- 2 days- 22 participants |  |  | 3200 |  |  |  | Price to be determined by Supply
| Training of Trainers (ToT) for Gov and SMS partners- 4 days-20 participants |  |  | 6400 |  |  |  | Price to be determined by Supply
| Training of Trainers (ToT) for Gov and SMS partners- 4 days-20 participants |  |  | 6400 |  |  |  | Price to be determined by Supply
| Training of Trainers (ToT) for Gov and SMS partners- 4 days-20 participants |  |  | 6400 |  |  |  | Price to be determined by Supply
| 5 Videos dubbing (English to Bangali) |  |  | 2500 |  |  |  | Price to be determined by Supply
| Translation of CCCM Materials (10 modules, ppt and session plans) |  |  | 3000
| Distribution centers KTP/NPR/CKM | 1 |  | 500000 | 2018-03-01 | Designs done, go to tender late Jan 2017 | Shelter/Site Planning | Frame agreement in place for: 62,000USD for WP#14
| Nayapara Road and NYP Site Development | 1 |  | 300000 | 2018-03-01 | Designs done, go to tender late Jan 2017 and WP yet to be submitted | Shelter/Site Planning | Tendering initiated for 190,000USD (2 roads for NYP) + 106,257USD (PO under FA)
| Framework Agreement | 1 |  | 4000000 | 2018-03-01 | Gone to tender | Shelter/Site Planning | FA to be established in January (process launched) for semi-perm.structures, road construction, drainage, construction material
| Additional Sandbags | 312000 |  | 273000 | 2018-04-01 | Reviewing current design before amending spec and launching | Shelter/Site Planning | BRAC will provide sandbags through PPAs; The need for sandbags is to complement Oper.Partners (ACF) + Caritas + OPS partners doing site development | not in OL
| Locks and Chains for shelters | 80000 |  | 230000 | 2018-03-01 | Testing 182 before seeking permission for full scale up | Shelter/Site Planning |  | not in OL
| Framework Agreement, assuming raise in OL | 1 |  | 4000000 | 2018-05-01 |  | Shelter/Site Planning |  | not in OL
| Site development of KTP zone AA | 1 |  | 218999 |  |  | Shelter/Site Planning
| Site development of KTP zone QQ | 1 |  | 143078.1 |  |  | Shelter/Site Planning
| DISASTER PREPARADNESS | [5 empty] | Shelter/Site Planning
| Pre-cyclone shelter Kit | 80000 | 8 | 640000 | 2018-03-01 |  | Shelter/Site Planning | Content of the kit: 06mm polypropylene rope - 1kg; Low carbon steel were 18-19 gauge - 1kg; Re-bur (12mmdia 80cm long) - 3.6kg; every HH should be covered with pre-cyclon kit
| Post-cyclone shelter repair kit (RSK) | 60000 | 19.68 | 1180800 | 4th quarter 2018 | assumption that rain season destroys 75% shelters; 40,000 plastic sheeting already within 2017 contingency stock; | Shelter/Site Planning | Content of the RSK: 06mm polypropylene rope - 1kg; Low carbon steel were 18-19 gauge - 1kg; plastic sheet - 1 pc
| Rubhalls for communal shelter | 20 | 14565 | 291300 | 3rd quarter 2018 | assumption that we need communal shelter | Shelter/Site Planning | Mass emergency shelter in an aftermath; they would be erected behind Transit Center | not in OL
| Construction of prepositioned emergency stock |  |  | 1500000 | 2nd quarter 2018 | construction of 2-3 safe sites for prepositioning of stock in case of natural disaster | Shelter/Site Planning | Including access, site development, structures, assuming that there will be no access to rubhalls and depending on the land availability; pre-fab steel structures; MSUs (mobile storage units will be set up by WFP) | to be discussed further
| Monthly coordination meetings with partners (30 participants each) | 12 |  | 1000 |  | Costs of refreshment and lunch/office | Programme
| Regular meetings with partners and stakeholders | 400 |  | 5000 |  | Cost of refreshment/office | Programme
| Capacity building for partners-Programme Management and Project Control Training (50 participants each) | 3 |  | 3000 | 1st training to be held on 5-6 February | Venue outside the office; lunch, refreshment, handouts | Programme
| Construction of Temporary Learning Centers (TLCs) | 50 |  | 250000 | February/March | TLCs including latrines | Education
| Quick Impact Projects/CSP | 1 |  | 250000 | As soon as QIPs are developed | Construction/infrastructure for host community - TBD | Education
| Capacity building for community governance structures | 45 |  | 6750 | March, June, November | e.g. leadership, community consultations, gender sensitive decision making, empowerment of women leaders, etc. | CB Protection
| Capacity building for community groups | 45 |  | 6750 | February, May, October | e.g. participation, planning and organization, supporting persons with disabilities, empowerment of women, etc. | CB Protection
| Community Group initiatives serving their communities | 180 |  | 36000 | Monthly | e.g. assistance to PSN, improved living environment, activities for children, etc. | CB Protection
| Awareness raising activities for key topics and international days | 180 |  | 45000 | Monthly | e.g. Persons with Disabilities, Older Persons, Women, Youth, Human Rights, etc. | CB Protection
| Capacity building for Partner staff in Cox's Bazar | 4 |  | 8000 | Quarterly | e.g. Community Empowerment, PSN support, and Program management, etc. | CB Protection
| Capacity building for Partner staff in field locations | 60 |  | 9000 | Quarterly | " | CB Protection
| Tablet for COMs | 130 |  | 15600 | December | Tablets for COMs Team in 10 locations | CB Protection
| Tablets for Information points | 27 |  | 3240 | January | Tablets for 15 information points | CB Protection
| Materials for information and awareness raising | 12 |  | 2500 | December | Translation and production | CB Protection
| Partner/COM Team Leaders capacity building activities | 8 |  | 1500 | Monthly | 8 workshops - for approx. 30 people (500 Taka per person X 30 people X 8 workshops) | CB Protection
| Half year retreats with COMs/Partners | 2 |  | 12000 | December | 3 locations (8oo Taka per person X 300 people X 2 retreats) | CB Protection
| Translation services | 52 |  | 3900 | Monthly | estimated 5 hours of translation average per week at $15 per hour | CB Protection
| Bulk SMS for information to refugees | 12 |  | 3000 | Monthly | estimated 100,000 SMS per month at $0.25 per 100 SMS | CB Protection
| Hand crank AM/FM radios | 5000 |  | 75000 | April | estimated 5,000 families for pilot at $15 per radio | CB Protection
| Training workshops for 25 UNHCR and partner staff | 6 | 1000 | 6000 | 1 on average every other month | Cost for venue at hotel, lunch and refreshments | Child Protection | Estimated price provided
| Training workshops for 30 community members in camps | 6 |  | 3000 | 1 on average every other month | Cost for lunch and refreshments | Child Protection | Estimated price provided
| Snacks for meetings with30 members of the community | 200 meetings |  | 12000 | throughout the year | 1 drink, 1 banana, 1 sweet/cookie for each participant. Meetings held in 6 different locations on average once a week. | Child Protection | Estimated price provided
| Printing of posters for community centers | 50 |  | 5000 | throughout the year | 11 community centers finalized/planned, others will come | Child Protection | Estimated price provided
| Translation of powerpoint presentations and guidelines | 500 pages |  | 2500 | Half by 31 March, other half by 30 June | These are to be used for child protection training with partners and refugee community | Child Protection | Estimated price provided
| Construction of Overhead Tank and Solar Pumping-Nayapara | 1 |  | 200000 | 2018-06-01 |  | WASH
| Construction of Drianage - Nayapara | 1 |  | 30000 | 2018-03-01 |  | WASH
| Construction of Drianage - Kutupalong | 1 |  | 15000 | 2018-10-01 |  | WASH
| Construction of Retaining Wall at Nayapara Reservoir | 1 |  | 31250 | 2018-04-01 |  | WASH
| Repair Maintenace of Silt Trap Facilities | 1 |  | 6400 | 2018-04-01 |  | WASH
| Water Trucking at Nayapara in Nayapara RC | 1 |  | 50000 | 2018-04-01 |  | WASH
| Capacity Development (Different Training) | 3 |  | 6000 | 2018-04-01 |  | WASH
| Reagent Accessories for Water Quality Test | 1 |  | 3900 | 2018-04-01 |  | WASH
| Contingency Hygiene Kit | 5000 | 35 | 175000 |  | Standard package of HK as contigency for AWD | WASH
| Energy | [5 empty] | WASH
| O&M contract of Mini Grid | 1 |  | 11900 | 2018-02-01 |  | WASH
| Intallation of Panel Cleaning System for Mini Grid in both camp | 1 |  | 3000 | 2018-03-01 |  | WASH
| Procuremt of Equipment and accessories for Mini Grid | 1 |  | 4000 | 2018-06-01 |  | WASH
| Procurement of 10,000 CRIs as contingency (new arrivals) | 10000 | 180 | 1800000 | 2018-06-01 | Support in CRIs for 10,000HH in the monsoon/cyclon aftermath; In addition, contingency stock of 15,000 CRIs in place. | Field |  | not in OL
| Procurement of LPG and assessment on energy |  |  | 1250447.7381 | 2nd half of the year | 2212130.6346 | Field/Supply
| Procurement of CRH for 04 months |  |  | 1200000 |  |  | Field/Supply
| LPG pilot project for 2000HH |  |  | 400000 | April |  | Field/Supply
| Hiring of buses for relocation of PoC |  |  | 110279.1014 | For entire year |  | Supply/Logistics
| Hiring of trucks for relocation of PoC |  |  | 10619.47 | For entire year |  | Supply/Logistics
| Construction materiials (distribution point in Nayapara, additional works at Uttaran, purchase of ropes) |  |  | 66116.6594 | Jan and Feb 2018 |  | Supply/Logistics
| Road Cargo Transport for relief items (2017) |  |  | 120321.9011 | Jan and Feb 2018 |  | Supply/Logistics
| Warehouse rental (Uttaran) |  |  | 50498.1744 | For entire year |  | Supply/Logistics
| Warehouse security |  |  | 65866.6997 | For entire year |  | Supply/Logistics
| Warehouse labor (kitting, loading, offloading) |  |  | 55250.9437 | For entire year |  | Supply/Logistics
| Transportation of CRIs in the camp (local transport) |  |  | 167308.08 | For entire year |  | Supply/Logistics
| Road and marine transport for international shipments |  |  | 638004 | For entire year |  | Supply/Logistics
| Rental of land in Nayapara for establishing rub hall and distribution center |  |  | 7426.2021 | For entire year |  | Supply/Logistics
| Logistics/warehouse items: water tanks structures, forklifts, cameras, fans, etc. |  |  | 10000 | February 2018 |  | Supply/Logistics | Input pending
| Tender advertisment costs |  |  | 5000 |  |  | Supply/Logistics
| Procurement training for partners |  |  | 1500 | February |  | Supply/Logistics
| Trainings | 5 | 2000 | 10000 | June | Training programs for CiCs, judicial officers, police, military and partner staff. | Protection (general) | Input pending
| PI Items |  |  | 10000 |  |  | PI/External Relations | Input pending
| Grand Total |  |  | #VALUE!
Note on E150: Yewubdar Mekasha: USD 200,000 increase; Jelena Mazic: initial submission 600,000; decreased based on the technical mtg held on 28 Jan
Note on C152: Yewubdar Mekasha: 62,000 more added for Chakmakul

## Chaks (hidden)
Generator 25 KVA, UPS suppoort.
- Generator equipment, (Motor oil, Cooling water)
- Generator movement cost.
- Generator setup cost.
- Verification assistance (TAI) *40
- UPS for Card printer/ Stabilizer for card printer.
- UPS for network equipment. ( need quite large one. )
- Network equipment.
- Card printer ( Max 400 a day on full operation. around 300 should be used to calculate.)
- plastic card, transfer flim, lamination.
- BIMS light.
- UPS
- Labtop
- Wire.
- RCB.
- Breaker.
- SSD harddisk for W541.
- SSD harddisk for proGres server in IT room.
- adapter for W541.
- Rub hall equipment.
- Shelter taging sticker.

## ABOD (hidden)
2018 Procurement Plan
SL | Description of the Goods / Services | Quantity | Value per unit (in USD) | Expected value, USD | Expected date of completion | Remarks | Sector | Budget
| Plotter (Printer / Scanner) |  |  |  | 31/01/2018 - 31/03/2018 | To scale-up IM support to the operation and partners's need of large-scale printing of maps, interactive dashboard, and other IM products | IM | ABOD
| Trimmer |  |  |  | 31/01/2018 - 31/03/2018 | To cut marging of printed document at larger size | IM | ABOD
| Roll paper - A0 size | 1 year supply |  |  | 31/01/2018 - 31/12/2018 |  | IM | ABOD
| Ink for plotter printer | 1 year supply |  |  | 31/01/2018 - 31/12/2018 |  | IM | ABOD
| Adobe Illustrator License | 3 | 29.99 / month / license | 1079.64 | 01/02/2018 - 28/02/2018 | To alllow larger staff members to create visualization product efficiently (e.g. Power BI to PDF design) | IM | ABOD
| Acrobat Pro License | 6 | 14.99 / month / license | 1259.16 | 01/02/2018 - 28/02/2018 | To allow staff to provide quick and highquality PDF through direct edits and other formatting | IM | ABOD
| 27-Inch 4k Screen LED-lit Monitor | 1 | 500 | 500 | 31/01/2018 - 31/03/2018 | High resolution and large screen monitor can improve the quality and the efficiency of design work | IM | ABOD
| Upgraded work station / desktop | 4 | 500 | 2000 | 31/01/2018 - 31/03/2018 |  | IM | ABOD
| Mini / pocket projector | 1 | 20 | 20 | 31/01/2018 - 31/03/2018 | Providing visual supports during capacity building program (field and office) | IM | ABOD
| SMU office support | [5 empty] | Site Management | ABOD
| Printer (A3/A4) | 1 | 490 | 490 | 2018-01-30 | Smart printer with scanner, copy, and printing | Site Management | ABOD
| Paper | 20 | 5 | 100 | 2018-01-30 | at least for one year | Site Management | ABOD
| Stationery (office) | 1 | 100 | 100 | 2018-01-30 | Pens, scissor, tape, flipchart, marker, flipchart stand, notebook | Site Management | ABOD
| Table | 2 | 100 | 200 | 2018-01-30 | for new 2 international staff | Site Management | ABOD
| Smart Chair | 2 | 100 | 200 | 2018-01-30 | for new 2 international staff | Site Management | ABOD
| Tablets | 6 | 250 | 1500 | 2018-01-30 |  | Site Management | ABOD
| GPS Garmin | 5 | 210 | 1050 | 2018-01-30 |  | Site Management | ABOD
| Meeting table | 1 | 200 | 200 | 2018-01-30 |  | Site Management | ABOD
| Meeting table Chairs | 8 | 100 | 800 | 2018-01-30 |  | Site Management | ABOD
| Cabinet | 2 | 90 | 180 | 2018-01-30 | for filing and archiving office related documents | Site Management | ABOD
| Site level data engagement | [5 empty] | Site Management
| Server | 2 | 2100 | 4200 | 2018-01-30 | two server at Cox's bazar and Kutupalong offices | Site Management | ABOD
| Accessories and equipment for Server at KTP |  | 950 | 950 | 2018-01-30 | Air Condition, table, chair, cabinet, multichords etc. | Site Management | ABOD
| Solar panel for individual post | 10 | 1640 | 16400 | 2018-01-30 | solar panel along with stands and router | Site Management | ABOD
| Solar panel for server | 2 | 1640 | 3280 | 2018-01-30 | Back up for server at Cox's bazar and Kutupalong offices | Site Management | ABOD
| ISP | 12 | 1000 | 12000 | 2018-01-30 | internet access at Kutuplong server and the end users within Kutupalong entire zones | Site Management | ABOD
| Desktop computer | 4 | 1100 | 4400 | 2018-01-30 | Desktop computers as a data inputs, data syncronization, and storage at Cox's bazar, Kutupalong and two sites | Site Management | ABOD
| Tablets | 40 | 250 | 10000 | 2018-01-30 |  | Site Management | ABOD
|  |  | Total | 51230

## Annex A
ANNEX A BGD-UNHCR RFQ 3583 FOR THE SUPPLY AND DELIVERY OF FUEL (DIESEL) FOR GENERATORS AND VEHICLES TO THE BHASANCHAR, HATIYA, NOAKHALI, BANGLADESH
SL | Item Name and Detailed Specifications | Unit of Measure | Total Quantity (Three years) | Unit Rate (BDT) (Excluding VAT) Delivery at Shelter 15, Bhasan Char (DPU) | Total Cost (BDT) (Excluding VAT) Delivery at Shelter 15, Bhasan Char (DPU) | Applicable VAT (%) | Delivery lead time (Days) after receiving PO
1 | FUEL (DIESEL) - in line with all-time Gazette | Liter | 72000 | (please mention the current Gazette price)
2 | Transportation, new metal containers, and all associated delivery costs to Cluster 15, Bhasan Char, Hatiya, Noakhali, Bangladesh Required Delivery Schedule: 6,000 Liter per quarter (Every three months) | EA | 12 |  | 0
TOTAL AMOUNT (BDT) |  |  |  |  | 0
By signing this Offer Form you acknowledge the UNHCR's General Terms an Conditions (Annex B), the UN Supplier's Code of Conduct (Annex C) and you confirm your offer is in line with UNHCR's requirements outlined in the tender documents. Note: Suppliers required to deliver 6000 Liters to Bhasan Char in every three (3) months and 4 times a year and 12 times in three years.
| Other info. pertaining to the offer | YES | NO (specify)
Currency of your Offer (BDT)
Payment Terms: acceptance of UNHCR payment terms - within 30 days after completion of delivery
Validity of Offer: your quotation must be valid for at least ninety [90] days
NAME:
IN THE CAPACITY OF:
DULY AUTHORIZED TO SIGN BID FOR
AND ON BEHALF OF:
DATE:
OFFICIAL STAMP:

## Sheet1 (hidden)
Displaying Screen : 10 inch
Operating System : Android Nougat 7.0 (minimum)
Resolution : 1280*800
CPU : Quad Core (Minimum 1.3 GHz)
RAM : 2GB DDR3 (Minimum)
ROM: 8 GB
Battery: 4500 mAh
Camera: 5 MP
Displaying Screen : 10 inch Operating System : Android Nougat 7.0 (minimum) Resolution : 1280*800 CPU : Quad Core (Minimum 1.3 GHz) RAM : 2GB DDR3 (Minimum) ROM: 8 GB Battery: 4500 mAh Camera: 5 MP